AFRINREN Meeting 7 with Hussein Suleman

Project

- Project plan decided. Hussein will email to us (hopefully).

  - Iteration 1 (Start next week - 3 weeks long): Requirements Gathering

    - Design (Paper Prototype?)

    - Implement

    - Evaluate

  - Iteration 2: Consult with users

  - Iteration 3

Design

Experimentation

Evaluation

Project Report

- Hussein estimates report should take just over a week to write report

- 10 pg ACM format

Points of Action:

- Work on background chapter (should be page to page and a half)

- Carry on working on each of our sections independently

- Next week decide on method for user requirements gathering

  - Survey? Obtain mailing list of people from African Network Community (Ask Josiah?)

  - Interview?

  - Focus Group?

- Start formulating questions for survey and/or interviews

- Run past Hussein and Josiah

Due Dates:

- 7 Aug: Lit Review Section of Report Due

- Dedicated project block starts on 21 August

- 25 September: Design Section Due - Statement of Design Process and Final Design

- 16 October: Final Draft of Report

- 26 October: Final Project Submission (Code + Report)

Next Meetings (Hussein away for 3 weeks):

- 30 July Thursday 11am-12pm

- 6 Aug Thursday 11am-12pm